AGENDA

- Draft letter for Amendment of the contract

- Proposed new time frame

- A report on data collection, detailed maps and ground truthing, showing decadal trends in biodiversity loss and gain in Tanzania 25th January 2026

- Data collection (physical, biological, geomorphological, socioeconomic data and marine resource use) in Mkuranga and Mkoani, development of map layers, and data ground-truthing. 25th January 2026

- Validation meeting: 28 February 2026

- A comprehensive economic valuation report of coastal and marine ecosystem goods and services in Mkuranga and Mkoani districts, including spatial mapping of classified assets, comparative risk analysis, baseline valuation in USD across key ecosystem service categories, identification of data gaps, collection of additional field data, and stakeholder-validated recommendations to support bio-economic modeling and investment planning. 31st March 2026

- A detailed cost-benefit analysis report evaluating proposed bioeconomic activities in Mkuranga and Mkoani,

- including financial feasibility assessments, recommended green/blue finance instruments, and policy guidance to

- support blue economy growth, biodiversity conservation, and ecosystem resilience in alignment with national

- climate action plans.31st March 2026

An interactive digital visualization tool—including a dashboard, web maps, and story maps—illustrating marine biodiversity loss and gain across Tanzania, with focused visualizations and key statistics on ecosystem status in Mkuranga and Mkoani districts, using data from geospatial mapping and ecosystem valuation analyses. 1st Dec 2025- 15 April 2026

- Identify the key person/contact person in Mkuranga + Mkoani (proposed to have a person from Zanzibar)

- Mkuranga- Ms. Lucia- District Fisheries Officer

- Mkoani- Dr. Hamza-

- Introducing the project to the District authorities: (The letter will include the introduction of the project, proposed date for field data collection, and stakeholders' data validation meeting)

- TAMISEMI letter/ VPO_Letter

- Preparation of the Draft- Mpina to lead- validation meeting)

- Data collection plan (Types, who is collecting what? And where)

- Does existing data meet to the given objective

- A comprehensive economic valuation and  cost-benefit analysis to be combined

- Geospatial Mapping (GIS & Remote Sensing)- Mangrove ecosystems- This is available – Seagrass + Coral reef – whole coastline

a. Use high-resolution remote sensing and GIS to:

i. Develop marine biodiversity (Mangroves)  loss or gain spatial trend maps for Tanzania's coastal and marine- Mangrove only

areas.

ii. Map out areas in each coastal district of the United Republic of Tanzania requiring

restoration as additional inputs for carbon offset schemes and climate mitigation.

After having the loss and gain, it will be possible to show the extent of restoration of the Mangrove (We can prepare a table to summarise the findings)

iii. Carry out ground-truthing, incorporating local knowledge to validate the biodiversity loss (mangrove), and gain maps and degraded hotspots.

- Consult the Mangrove network

- ESA data- 10m resolution ( Land cover for the whole area)

- NAFORMA (land cover for the whole area)

Pamba to lead this WP under the guidance of Semba.

Develop interactive GIS-based maps layers of Mkuranga district and Mkoani district

(Southeast Pemba) covering:

i. Physical and oceanographic features: bathymetry, seabed morphology, ocean currents, sea

level trends, salinity, temperature, acidification, upwelling zones.

ii. Ecological and biodiversity assets: mangroves, seagrasses (Allen Atlas), coral reefs, beaches, rocky shores, critical fish habitats (questionnaires) , migratory corridors (e.g. turtles, sharks), designated/proposed MPAs (Pamba).

iii. Health indicators represented by habitat degradation,

- We need more information.

- pollution hotspots- Review is needed to identify the hotspots

- overfished zones (Prawns- Zone II) (look for a layer to show that zones)

- areas of climate change vulnerability and risks

(Area that will be affected by the rise of sea level)- Area below 1m or 5m from the sea level (HB- report)

- oil spill sensitive areas

We can use the TAN-Sea map

iv. Human activities:

Settlements- (types of towns)- Consultation

infrastructure

ports (Fish landing sites)

aquaculture zones/ Mariculture sites (Seaweeds, Crab fattening, (Matango bahari)

tourism hubs,

ECAS- data (Catch data + Value landing sites)

(QGIS- plugin open street maps)- Pamba

Alternative livelihoods (e.g. seaweed farming), (Initiative to reduce marine pressure)

industrial uses (use the open street map, consult the district surveys)

Fishing areas (Grounds)- Use Fish pattern mapping (Heshimu Bahari)

Fish landing points,

Collaborative Fishery Managed Areas (CFMA)

Collaborative Management Areas (CMA),

Beach Management Units (Frame survey)

Oil and gas (Wells and blocks) - (TPDC)

- Secondary data collection – Interactive GIS ( sources and type of data, etc., accompanied by a report of Mkuranga and Mkoani)

- Semba to lead this WP with the guidance of Pamba

- While ensuring compliance with open data standards, interoperability, metadata protocols, and user accessibility for integration with mobile/web platforms, perform geospatial analysis of the map layers in 1(b) above supplemented by stakeholder engagement in Mkuranga and Mkoani district (Southeast Pemba) to map out:

a. Areas of potential marine resource-use conflicts.

b. Areas or zones vulnerable to climate shocks.

c. Ship navigation routes.

d. Community-priority conservation areas, fisheries closure areas, designated community-level marine parks, designated/proposed blue carbon areas, and areas with opportunities for eco-tourism.

e. Presentation of the map layers obtained from 1 and 2 to local and district stakeholders for validation and endorsement. (Validation meeting/workshop)

- Mpina to lead this WP with the guidance of Semba and Pamba

- Undertake economic valuation of marine ecosystems goods and services, and potential investment opportunities in Mkuranga district and Mkoani district.

- Mangrove, coral (Mkuranga is limited)

- Focus on the key habitats (Mangroves, coral and seagrasses) + Beaches

- Existing data to estimate market value

- Area covered by key habitats

a. Classify and catalog coastal and marine assets, their ecosystem goods and services to provide background and context for the area by mapping the available data in Mkuranga and Mkoani districts

b. Conduct ecosystem services analysis through comparative risk analysis of the ecosystems

(under provisioning services, cultural services, regulating/supporting services) and prioritize the

ecosystems for further valuation in terms of food provisioning, raw materials provisioning, carbon sequestration, ecotourism and recreation, regulation of extreme events, and scarce habitats.

c. Conduct a baseline ecosystem services valuation quantifying the revenue generated in US dollars for:

i. food provisioning from marine fish catch, mariculture, and agriculture

ii. The gathering of raw materials, particularly fuelwood and timber

iii. cultural services of tourism and recreation

iv. carbon sequestration services

v. regulating services related to the maintenance of scarce habitats

vi. The regulation of extreme events

d. Identify gaps in 3(iii) above, requiring additional collection of field data in Mkuranga and

Mkoani, and actual data collection, and presentation to stakeholders to support the construction

of the relevant bio-economic models

Maro to lead this WP with assistance from Julius

- Following the ecosystem services valuation in 3 above, conduct a cost-benefit analysis to

evaluate the benefits of implementing proposed bioeconomic activities (e.g. new MPA, carbon

offset co-managed sites, octopus closure sites, seaweed farming plots, pelagic anchovies

(dagaa) etc in Mkuranga and Mkoani), and the costs of implementation

- Look for the Data required at the District level.

a. Propose green/blue finance instruments for funding management plan and implementation of

proposed bio-economic activities

- Propose how will be funded. (E.g. Local tax, private investors etc)

b. Recommend further policy measures and management interventions required to enhance (i)

blue economy opportunities, (ii) inputs to national biodiversity conservation strategies, and

action plans for protecting biodiversity and ecosystem services, and (iii) options for resilience

of the ecosystem towards national climate action plans, outlining how Tanzania plans to reduce

greenhouse gas emissions and adaptation to climate change

- Upscale

- Linked with 4a

Mpina to lead with the inputs from other members.

- Environmental dashboard

a. Provide a detailed dashboard displaying:

i. story maps and web maps for visualizing marine biodiversity loss and gain.

ii. maps showing degraded hotspots in Tanzania requiring restoration.

iii. webmaps, and story maps with data drawn from 1 and 2 above for the visualization of the state of Mkuranga and Mkoani districts.

iv. Valuation of ecosystems goods and services in Mkuranga and Mkoani districts.

v. Cost-benefit analysis for implementation of environmental and socioeconomic measures to accelerate blue economy initiatives and innovations.

Budget: Mpina

Validation meeting

Data collection: Pemba + Mkuranga

- Job: Financing and admin issues